## Slide 1
Cover Oregon
HIX Delivery Metrics
April 16, 2013

## Slide 2: Overall Status Updated: April 16th, 2013
R
Area | Status | Comments
i17 Development | R | Velocity slowed this week, trending at 51% against target of 71% for 4/30 (72% of goal). Causes: 1) No longer stubbing interfaces, changes have a greater impact, more thrashing, 2) Changing requirements – external data, interfaces Freeze on Changes as of 4/10.
Change Control | Y | 86 Changes to-date
Issue/Defect Mgmt | Y | 276 Total Issues (15 Blockers, 100 Critical)
HIX Scope/Delivery Issues/Items Causing Delay:
Interface testing taking up a lot more time than anticipated due to state of delivered interfaces.
Account Management - developing off of process flow vs. fully documented use cases.
“Shaking and Baking the Requirements” session scheduled for 4/18.
Interface hand-off process implemented - need to drive compliance to the process

## Slide 3: Delivery Status (continued) Updated: April 9th, 2013
R
Reminder - Core 4/30 scope includes the following:
  EE (minus tribal members, minus Medicaid)
  SHOP (employer & employee)
  AM (minus authorized users)
  PM (minus dental plans, minus carrier verification and dashboard)
  Any FM we can accomplish
  Any CS we can accomplish

## Slide 4: Development Velocity Updated: Data as of April 10, 2013
R
i17 LOE Velocity only
LOE changes due to discovery during development, CRs
Working on additional views

## Slide 5: Development Velocity Updated: Data as of April 10, 2013
R
Consolidated LOE (i14 to i17)

## Slide 6: Functional Area Updated: Data as of April 14 , 2013
R
Percent Complete by Functional Area (4/14/13) |  |  | 
Functional Area | LOE | LOE Complete | % Complete
Account Mgt | 194.04 | 106.61 | 54.95%
Community Partners | 245.46 | 66.73 | 27.19%
Customer Service | 513.09 | 296.83 | 57.85%
Eligibility | 678.72 | 364.10 | 53.65%
Enrollment | 449.06 | 255.86 | 56.98%
Financial Management | 1763.12 | 1078.10 | 61.15%
Plan Mgt | 426.22 | 224.56 | 52.69%
SHOP | 1625.84 | 1163.50 | 71.56%
Tribal | 413.09 | 351.02 | 84.97%
Global | 592.79 | 447.08 | 75.42%
All Functions | 6901.41 | 4354.40 | 63.09% *
* Should be at 68.2% - analyzing the calculations

## Slide 7: Change Control Updated: April 15th, 2013
Y
7
Total
Changes:
Types of
Changes:
Freeze as of April 10 for 4/30 delivery.
Processed 8 new change requests: 7 Major and 1 Minor
1 Major request covers multiple Account Management process flows used in lieu of complete use case packages; the use cases packages are still to be delivered
JIRA ticket resolution requiring changes to UCs, etc. and
Changes coming through Scope Management Meeting.
Type | Status as of 4/15 | Previous Week | WoW Change
Major | 56 | 49 | +7
Minor | 30 | 29 | +1
TOTAL | 86 | 78 | +8
Artifact | Status as of 4/15 | Previous Week | WoW Change
Use Case Doc | 51 | 47 | +4
BRD | 16 | 15 | +1
Data Def Doc | 16 | 14 | +2
UI | 34 | 33 | +1

## Slide 8: JIRA/Issue Status Updated: April 15th, 2013
JIRA clean-up continues – meeting with BA’s, improving reporting process
Includes FS tickets
Y
Type | As of 4/15 | Prev Week | WoW Change
Blockers | 15 | 14 | +1
Critical | 100 | 98 | +2
Major | 128 | 143 | -15
Minor | 33 | 31 | +2
Trivial | 0 | 0 | 0
Total Open JIRA | 276 | 286 | -10
Issue Count By Area
Issue Count By Age
Chart: 
| 0-10 | 011-020 | 021-030 | 031-040 | 041-050 | 051-060 | 061-070 | 071-080 | 091-100 | 101-110 | 121-130 | 151-160 | (blank)
Blocker | 4 | 5 | 5 | 1
Critical | 45 | 28 | 2 | 16 | 7 | 1 | 1
Major | 20 | 21 | 19 | 43 | 3 | 8 | 3 | 6 | 2 | 1 | 1 | 1
Minor | 7 | 8 | 6 | 1 | 1 | 1 | 9
(blank)
Chart: 
| AM | CPA | CS | EE | FM | PM | SHOP | TP | (blank)
Blocker | 1 | 4 | 2 | 1 | 2 | 5
Critical | 4 | 16 | 1 | 8 | 15 | 21 | 35
Major | 4 | 8 | 14 | 17 | 24 | 8 | 12 | 10 | 31
Minor | 1 | 2 | 10 | 1 | 9 | 1 | 9
(blank)

## Slide 9
Appendices

## Slide 10
Issues/Risks Log

## Slide 11
EE
AM
PM
SHOP
TP
Eligibility
Plan Selection
Enrollment
Tribal Member
Medicaid
FM
(Psft)
CS
Lower
priority
Employer
Employee
Entity
TIME
CP
I-17 Dev Prioritization
Direction Guidance
Change in Circumstance
Some parallel
Top to Bottom
Left to Right